## Road Map
Streamfeeder
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 1/29/21 | Iteration 2 - 3/30/21 | Iteration 3 - 4/25/21 | Iteration 4 - 5/1/21
Module 1 - User Account | 01.01 Onetime login | n/a
| 01.02 Ability to manage multiple social media accounts at once | 10 | x
| 01.03 Easily upgrade to premium subscription | 8 |  |  |  | x
| 01.04 Create an account | 4 | x
Module 2 - Posting New Content | 02.01 Ability to create and add a post | 6 |  |  | x
| 02.02 Create and add a comment to a post | 6 |  |  | x
| 02.03 Like and dislike a post | 5 |  | x
Module 3 - Saving Content | 03.01 Bookmarking posts for later review | 8 |  |  |  | x
| 03.02 Page to view saved content | 7 |  | x
Module 4 - Browsing Content | 04.01 Infinite scrolling to browse channels | 5 |  | x
| 04.02 Dedicated page to view content | n/a
| 04.03 Easily copying link of desired post for sharing | 1 | x
| 04.04 Intuitive landing page not requiring user account | n/a
|  | Velocity : | 15 | 17 | 12 | 16