## Sheet1
Task# | Module Name | RCT ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Iteration
1 | User Account | 1.04 | Creating Account | Landing page for GUI | 02-19-2021 | 02-23-2021 | 100% | Stephen Cahill | I1
2 | User Account | 1.04 | Creating Account | Integrating with backend | 02-19-2021 | 02-23-2021 | 100% | Stephen Cahill | I1
3 | User Account | 1.04 | Creating Account | Checking updated data after login | 02-19-2021 | 02-23-2021 | 100% | Daniel Terach | I1
4 | User Account | 1.04 | Creating Account | Create test cases | 02-23-2021 | 02-23-2021 | 100% | Manisha Shinde | I1
5 | User Account | 1.04 | Creating Account | Execute test cases and document the test execution log | 02-23-2021 | 02-23-2021 | 100% | Daniel Terach | I1
6 | User Account | 1.02 | Ability to manage multiple social media | Implementing API | 2021-05-03 | 03-26-2021 | 100% | Stephen Cahill | I2
7 | User Account | 1.02 | Ability to manage multiple social media | GUI implementation | 2021-05-03 | 2021-12-03 | 100% | Stephen Cahill | I2
8 | User Account | 1.02 | Ability to manage multiple social media | Keeping data even after loss of network | 2021-05-03 | 03-26-2021 | 50% | Stephen Cahill | I2
9 | User Account | 1.02 | Ability to manage multiple social media | Create test cases | 03-26-2021 | 03-26-2021 | 100% | Manisha Shinde | I2
10 | User Account | 1.02 | Ability to manage multiple social media | Execute test cases and document the test execution log | 03-26-2021 | 03-26-2021 | 100% | Prajakta Jathar | I2
11 | Browsing Content | 4.03 | Easily copying link of desired post for sharing | Button to share posts | 2021-05-03 | 2021-12-03 | 100% | Sumant Watekar | I2
12 | Browsing Content | 4.03 | Easily copying link of desired post for sharing | Implementing social sharing feature | 2021-05-03 | 2021-12-03 | 100% | Daniel Terach | I2
13 | Browsing Content | 4.03 | Easily copying link of desired post for sharing | Create test cases | 2021-12-03 | 2021-12-03 | 100% | Manisha Shinde | I2
14 | Browsing Content | 4.03 | Easily copying link of desired post for sharing | Execute test cases and document the test execution log | 2021-12-03 | 2021-12-03 | 100% | Prajakta Jathar | I2
15 | Saving Content | 3.02 | Page to view saved content | Creating a page | 2021-05-03 | 03-19-2021 | 100% | Daniel Terach | I2
16 | Saving Content | 3.02 | Page to view saved content | Implementing a button for the page | 2021-05-03 | 03-19-2021 | 100% | Stephen Cahill | I2
17 | Saving Content | 3.02 | Page to view saved content | Button to pass the data to saved page | 2021-05-03 | 03-19-2021 | 100% | Stephen Cahill | I2
18 | Saving Content | 3.02 | Page to view saved content | Create test cases | 03-19-2021 | 03-19-2021 | 100% | Manisha Shinde | I2
19 | Saving Content | 3.02 | Page to view saved content | Execute test cases and document the test execution log | 03-19-2021 | 03-19-2021 | 100% | Prajakta Jathar | I2
20 | Posting New Content | 2.03 | Like and dislike a post | Adding a like and dislike button to the UI | 2021-05-03 | 03-19-2021 | 100% | Daniel Terach | I2
21 | Posting New Content | 2.03 | Like and dislike a post | Integrating with the core app | 2021-05-03 | 03-26-2021 | 100% | Stephen Cahill | I2
22 | Posting New Content | 2.03 | Like and dislike a post | Create test cases | 03-26-2021 | 03-26-2021 | 100% | Manisha Shinde | I2
23 | Posting New Content | 2.03 | Like and dislike a post | Execute test cases and document the test execution log | 03-26-2021 | 03-26-2021 | 100% | Prajakta Jathar | I2
24 | Browsing Content | 4.01 | Infinite scrolling page | Implementing GUI | 2021-05-03 | 03-26-2021 | 100% | Stephen Cahill | I2
25 | Browsing Content | 4.01 | Infinite scrolling page | Getting data from API for infinite scrolling page | 2021-05-03 | 03-26-2021 | 100% | Dachao Zhong | I2
26 | Browsing Content | 4.01 | Infinite scrolling page | Create test cases | 03-26-2021 | 03-26-2021 | 100% | Manisha Shinde | I2
27 | Browsing Content | 4.01 | Infinite scrolling page | Execute test cases and document the test execution log | 03-26-2021 | 03-26-2021 | 100% | Prajakta Jathar | I2
28 | Posting New Content | 2.01 | Ability to create and add a post | Implementing GUI | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
29 | Posting New Content | 2.01 | Ability to create and add a post | Implementing core feature | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
30 | Posting New Content | 2.01 | Ability to create and add a post | Implementing Entitlements | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
31 | Posting New Content | 2.01 | Ability to create and add a post | Data Flow in | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
32 | Posting New Content | 2.01 | Ability to create and add a post | Data Flow out | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
33 | Posting New Content | 2.01 | Ability to create and add a post | Implementing Exception Hadling | 03-26-2021 | 2021-09-04 | 80% | Stephen Cahill | I3
34 | Posting New Content | 2.01 | Ability to create and add a post | Create test cases | 03-26-2021 | 2021-09-04 | 100% | Sumant Watekar | I3
35 | Posting New Content | 2.01 | Ability to create and add a post | Execute test cases and document the test execution log | 03-26-2021 | 2021-09-04 | 100% | Manisha Shinde | I3
36 | Posting New Content | 2.02 | Create and add a comment to a post | Implementing GUI | 03-26-2021 | 2021-09-04 | 100% | Sumant Watekar | I3
37 | Posting New Content | 2.02 | Create and add a comment to a post | Implementing core feature | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
38 | Posting New Content | 2.02 | Create and add a comment to a post | Integrating with the core app | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
39 | Posting New Content | 2.02 | Create and add a comment to a post | Implementing Entitlements | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
40 | Posting New Content | 2.02 | Create and add a comment to a post | Data Flow in | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
41 | Posting New Content | 2.02 | Create and add a comment to a post | Data Flow out | 03-26-2021 | 2021-09-04 | 100% | Stephen Cahill | I3
42 | Posting New Content | 2.02 | Create and add a comment to a post | Implementing Exception Hadling | 03-26-2021 | 2021-09-04 | 80% | Stephen Cahill | I3
43 | Posting New Content | 2.02 | Create and add a comment to a post | Create test cases | 03-26-2021 | 2021-09-04 | 100% | Sumant Watekar | I3
44 | Posting New Content | 2.02 | Create and add a comment to a post | Execute test cases and document the test execution log | 03-26-2021 | 2021-09-04 | 100% | Manisha Shinde | I3
45 | User Account | 1.03 | Easily upgrade to premium subscription | Implementing GUI | 2021-09-04 | 04-30-2021 | 100% | Daniel Terach | I4
46 | User Account | 1.03 | Easily upgrade to premium subscription | Implementing core feature | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
47 | User Account | 1.03 | Easily upgrade to premium subscription | Implementing Entitlements | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
48 | User Account | 1.03 | Easily upgrade to premium subscription | Connectivity | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
49 | User Account | 1.03 | Easily upgrade to premium subscription | Data Flow Out | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
52 | User Account | 1.03 | Easily upgrade to premium subscription | Create test cases | 2021-09-04 | 04-30-2021 | 100% | Manisha Shinde | I4
53 | User Account | 1.03 | Easily upgrade to premium subscription | Execute test cases and document the test execution log | 2021-09-04 | 04-30-2021 | 100% | Sumant Watekar | I4
54 | Saving Content | 3.01 | Bookmarking posts for later review | Implementing GUI | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
55 | Saving Content | 3.01 | Bookmarking posts for later review | Implementing core feature | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
56 | Saving Content | 3.01 | Bookmarking posts for later review | Implementing Entitlements | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
58 | Saving Content | 3.01 | Bookmarking posts for later review | System Interface Out | 2021-09-04 | 04-30-2021 | 100% | Stephen Cahill | I4
59 | Saving Content | 3.01 | Bookmarking posts for later review | Create test cases | 2021-09-04 | 04-30-2021 | 100% | Manisha Shinde | I4
60 | Saving Content | 3.01 | Bookmarking posts for later review | Execute test cases and document the test execution log | 2021-09-04 | 04-30-2021 | 100% | Sumant Watekar | I4