## Initial Plan
Color Coding |  |  | Completed |  |  |  | CS 691 FALL 2020 SEMESTER - TEAM 5
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2020-08-24 | 2020-08-31 | 100%
| Confirm Project Team Roles |  | ALL | 2020-08-24 | 2020-08-31 | 100%
| Develop two business cases |  | ALL | 2020-08-24 | 2020-08-31 | 100%
| Develop Project Initiation Document (PID) |  | Manisha | 2020-08-31 | 2020-09-14 | 100%
| Produce initial Project Plan, RACI |  | Manisha/Steve | 2020-09-07 | 2020-09-14 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Sumant, Prajakta | 2020-09-14 | 2020-09-21 | 100%
| Produce Context Diagram, Define System Interfaces |  | Dachao, Daniel | 2020-09-14 | 2020-09-21 | 100%
| Define Business Requirements |  | ALL | 2020-09-21 | 2020-09-28 | 100%
| Agree to System Requirements types |  | Dachao | 2020-09-21 | 2020-09-28 | 100%
| Define Functional Decomposition |  | Daniel | 2020-09-21 | 2020-09-28 | 100%
| Produce RCT document |  | ALL | 2020-09-21 | 2020-09-28 | 100%
| Decide which features to implement this semester |  | All | 2020-09-28 | 2020-10-05 | 100%
| Produce analysis diagrams (UML, DFD) |  | Steve, Dachao,Prajakta | 2020-09-28 | 2020-10-05 | 100%
| Define functional requirements (User Stories) |  | Daniel | 2020-09-28 | 2020-10-05 | 100%
| Update Project Plan with additional requirements tasks |  | Manisha | 2020-09-28 | 2020-10-05 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Database Design (ERD, Table spec) |  | Prajakta | 2020-10-12 | 2020-10-19 | 100%
| Architecture design (2 diagrams) |  | Prajakta,Dachao | 2020-10-19 | 2020-10-26 | 100%
| System Interface Design |  | Dan | 2020-10-19 | 2020-10-26 | 100%
| User interface design |  | Steve | 2020-10-27 | 2020-11-10 | 100%
MILESTONE 3: DESIGN COMPLETED
Coding | Update project plan with additional requirements |  | Manisha | 2020-10-27 | 2020-11-03 | 100%
| Class Diagram |  | Dachao | 2020-10-27 | 2020-11-03 | 100%
| Sequence Diagram |  | Prajakta | 2020-10-27 | 2020-11-03 | 100%
| Source code sample, executable code ready for testing |  | Steve | 2020-10-27 | 2020-11-03 | 100%
| GUI & Functionality Detailed Design |  | Steve | 2020-10-27 | 2020-11-10 | 100%
| 01.01 One time login | Core functionality | Dachao | 2020-10-27 | 2020-11-10 | 100%
|  | GUI Features | Dachao | 2020-10-27 | 2020-11-10 | 100%
|  | ET- Entitlements | Dachao | 2020-10-27 | 2020-11-17 | 80%
|  | FV - Field Validation | Dachao | 2020-10-27 | 2020-11-10 | 100%
| 01.02 Ability to manage multiple social media accounts at once | Core functionality | Sumant | 2020-10-27 | 2020-11-17 | 50%
|  | GUI Features | Sumant | 2020-10-27 | 2020-11-17 | 50%
| 04.02 Dedicated page to view content | Core functionality | Steve | 2020-10-27 | 2020-11-10 | 100%
|  | GUI Features | Steve | 2020-10-27 | 2020-11-10 | 100%
|  | ET- Entitlements | Steve | 2020-11-03 | 2020-11-17 | 80%
| 04.04 Intuitive landing page not requiring user account | Core functionality | Steve | 2020-10-27 | 2020-11-10 | 100%
|  | ET- Entitlements | Steve | 2020-11-03 | 2020-11-17 | 80%
|  | GUI Features | Steve | 2020-10-27 | 2020-11-10 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Prajakta | 2020-11-03 | 2020-11-10 | 100%
| Evaluate Features to be Tested |  | Manisha | 2020-11-03 | 2020-11-10 | 100%
| Design Test Cases |  | Manisha | 2020-11-03 | 2020-11-10 | 100%
| Execute Test Cases |  | Daniel | 2020-11-03 | 2020-11-10 | 100%
| Anaylze Test Results |  | Daniel | 2020-11-03 | 2020-11-10 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2020-11-16 | 2020-11-23 | 0%